## PRIME_README
LUCTIV MAINTENANCE APP — V1 PRIME
Version | V1 PRIME — 2026-08-05
Source workbooks | Integrated_Pump_Failure_STT_Model_v1 + LUCTIV_Tabla_MTTO_Merged_Example
Purpose
This workbook is the data contract for the APP: it defines the front-end fields, the operational maintenance record, and the export structure after each fracturing stage. It contains no dashboard, ranking, score, or historical analysis.
Core data rules
1 | One row = one pump in one operational capture. | CaptureId groups all pumps in the same snapshot.
2 | CaseId persists while the same pump failure remains open. | A new capture does not create a new failure case.
3 | All broken or near-limit pumps remain visible. | PartOfPlan = Yes only for the units selected for the current STT.
4 | Planned and actual data are stored separately. | MinutesToRecovery is the estimate; ActualMinutes is calculated from the work clock.
5 | Exports are append-only. | Do not overwrite earlier stages; create a new CaptureId for each confirmed snapshot.
6 | Failure rules are starter rules. | Rules marked Draft require technical validation before automation.
Workbook structure
Pump_Stage_Log | Main operational table and APP export. Includes eight example units; only three are selected for the current STT.
Failure_Action_Catalog | Starter mapping from failure reason to condition, responsible group, action and reference time.
Catalogs | Controlled values used by front-end dropdowns and Excel validation.
Data_Dictionary | Technical definition of every field, its source, editability and landing-page visibility.
Landing page minimum view
PumpId ¦ Position ¦ CurrentStatus ¦ ConditionClass ¦ FailureReason ¦ ResponsibleGroup ¦ MinutesToRecovery ¦ PartOfPlan ¦ PlannedAction ¦ ReplacementPumpId ¦ WorkStatus
Smart Maintenance learning chain
Observed signal → failure characterization → responsible group → planned action → actual action → actual time → resolution outcome.

## Pump_Stage_Log
PUMP STAGE LOG — PRIME OPERATIONAL TABLE / APP EXPORT
RECORD & CAPTURE | [5 empty] | STAGE CONTEXT | [5 empty] | PUMP CONFIGURATION | [7 empty] | FAILURE CHARACTERIZATION | [8 empty] | CURRENT STT PLANNING | [7 empty] | EXECUTION & RESULT | [8 empty] | REAL-TIME OPERATION
RecordId | CaptureId | StageExecutionId | CaptureTimestamp | CapturedBy | CaseId | Pad | SetId | SpreadIdentifier | CrewName | Well | Stage | PumpId | PumpType | Manifold | ManifoldType | Position | PumpDistance | ActuatorNumber | DGB_Bifuel | CurrentStatus | ConditionClass | DetectionSource | FailureDetectedAt | FailureArea | FailureReason | FailureEvidence | DiagnosisStatus | ResponsibleGroup | PartOfPlan | STTOrder | STTReadiness | PlannedAction | ReplacementPumpId | MinutesToRecovery | TaskDescription | DeferredReason | WorkStatus | WorkStartAt | WorkEndAt | ActualMinutes | ActualAction | ConfirmedFailureReason | ResolutionOutcome | ReturnToServiceAt | Comments | PumpRate | PumpPressure | CleanRate | DirtyRate | JobRate | OffsetWellPressure
REC-0051-6672 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA |  | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 6672 | Fracturing pump | MFD-01 | Dirty | Left-05 |  | 22 | No | Rigged In - Working | Healthy / Available | Octiv |  |  |  |  | Not applicable |  | No |  | Not required | Stay Online |  | 0 | Continue operating |  | Not required | [5 empty] | Not applicable |  | Available during current stage | 4.5 | 8000 | 12 | 18 | 30
REC-0051-2268 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-2268-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 2268 | Fracturing pump | MFD-01 | Dirty | Right-06 |  | 12 | No | Rigged In - Not Working | Broken | Manual - Field | 2026-08-05 17:48 | Fluid end | Fluid End Maintenance | Unit unavailable; fluid-end maintenance required | Confirmed | PE | Yes | 1 | Ready | Rig Out | 2230 | 15 | Replace affected pump before the next stage |  | Selected current STT | [7 empty] | Sale por mantenimiento | 0 | 0 | 12 | 18 | 30
REC-0051-1951 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-1951-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 1951 | Fracturing pump | MFC-01 | Clean | Left-07 |  | 31 | No | Rigged In - Not Working | Almost / Consumable | Manual - Field | 2026-08-05 17:50 | Fluid end | Empaque | Packing condition identified during the stage | Confirmed | PE | Yes | 2 | Ready | Repair In-Line |  | 12 | Inspect and replace packing |  | Selected current STT | [7 empty] | Maintenance during current STT | 0 | 0 | 12 | 18 | 30
REC-0051-2230 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-2268-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 2230 | Fracturing pump | Spare | Off set | Off set |  |  | No | Rigged Out - Working | Healthy / Available | A360 |  |  |  |  | Not applicable | PE | Yes | 3 | Ready | Rig In |  | 5 | Replacement pump for Pump 2268 |  | Selected current STT | [7 empty] | Available spare selected for this STT | 0 | 0 | 12 | 18 | 30
REC-0051-8340 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-8340-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 8340 | Fracturing pump | Spare | Off set | Off set |  |  | No | Rigged Out - Not Working | Under diagnosis | Manual - Field | 2026-08-05 16:30 | Unknown | A base | Unit unavailable and sent for troubleshooting | Under diagnosis | IEM | No |  | Exceeds STT window | Send to Base |  | 120 | Unit sent to base for troubleshooting | Estimated recovery exceeds the current STT window | Deferred | [5 empty] | Deferred |  | Remains visible in backlog | 0 | 0 | 12 | 18 | 30
REC-0051-7720 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-7720-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 7720 | Fracturing pump | MFD-02 | Dirty | Left-08 |  |  | No | Rigged In - Working | Almost / Consumable | ACE | 2026-08-05 17:20 | Mechanical | Baja presión de lubricante | Power-end lube oil temperature oscillation warning | Suspected | Mechanical | No |  | Waiting diagnosis | Inspect |  |  | Inspect lubrication condition and confirm diagnosis | Not selected for the current STT | Backlog | [7 empty] | Near-limit condition; keep on backlog | 4 | 7800 | 12 | 18 | 30
REC-0051-4896 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-4896-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 4896 | Fracturing pump | MFD-02 | Dirty | Right-09 |  |  | No | Rigged In - Working | Operational condition | ACE | 2026-08-05 17:15 | Operations | Falla Operativa | High well pressure; target rate could not be maintained in the current gear | Confirmed | Operations | No |  | Not required | Monitor Next Stage |  |  | Adjust operating condition and monitor the next stage | Operational condition; no maintenance selected | Backlog | [7 empty] | Keep visible for operational follow-up | 3.5 | 10200 | 12 | 18 | 30
REC-0051-9800 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-9800-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 9800 | Fracturing pump | MFC-02 | Clean | Right-10 |  |  | No | Rigged In - Not Working | Broken | DPM | 2026-08-05 17:42 | E-tech / Controls | Falla sensor / instrumentación | DPM discharge sensor failure | Suspected | E-Tech | No |  | Waiting diagnosis | Diagnose |  |  | Inspect DPM sensor, wiring and signal | Waiting diagnosis before assigning STT work | Backlog | [7 empty] | Not selected for current STT | 0 | 0 | 12 | 18 | 30

## Failure_Action_Catalog
FAILURE → ACTION STARTER CATALOG
The three source-example rules carry source reference times. Other actions are Draft and require technical validation before automatic use.
RuleId | FailureReason | FailureArea | ConditionClass | ResponsibleGroup | SuggestedAction | DefaultMinutes | ReplacementRecommended | RuleStatus | SourceBasis | DefaultTaskDescription
RULE-001 | Fluid End Maintenance | Fluid end | Broken | PE | Rig Out | 15 | Yes | Source example | LUCTIV Tabla MTTO example | Replace affected pump before the next stage
RULE-002 | Empaque | Fluid end | Almost / Consumable | PE | Repair In-Line | 12 | No | Source example | LUCTIV Tabla MTTO example | Inspect and replace packing
RULE-003 | A base | Unknown | Under diagnosis | IEM | Send to Base | 120 | No | Source example | LUCTIV Tabla MTTO example | Send unit to base for troubleshooting
RULE-004 | Cavitación | Fluid end | Operational condition | Operations | Inspect |  | No | Draft - technical validation required | Classification from Integrated Pump Failure | Inspect suction and operating conditions
RULE-005 | Baja presión de lubricante | Mechanical | Almost / Consumable | Mechanical | Inspect |  | Depends | Draft - technical validation required | Classification from Integrated Pump Failure | Inspect lubrication system and confirm pressure condition
RULE-006 | Nivel de aceite incorrecto | Mechanical | Almost / Consumable | Mechanical | Inspect |  | No | Draft - technical validation required | Classification from Integrated Pump Failure | Correct level and inspect for leaks
RULE-007 | Falla DPM | E-tech / Controls | Broken | E-Tech | Diagnose |  | Depends | Draft - technical validation required | Classification from Integrated Pump Failure | Diagnose DPM condition
RULE-008 | Falla sensor / instrumentación | E-tech / Controls | Broken | E-Tech | Diagnose |  | Depends | Draft - technical validation required | Classification from Integrated Pump Failure | Inspect sensor, wiring and signal
RULE-009 | ACE / Windows / Daisy Data | E-tech / Controls | Broken | E-Tech | Reset / Reconfigure |  | No | Draft - technical validation required | Classification from Integrated Pump Failure | Reset or reconfigure control module and validate response
RULE-010 | Temperatura | Mechanical | Almost / Consumable | Mechanical | Inspect |  | Depends | Draft - technical validation required | Classification from Integrated Pump Failure | Inspect temperature, cooling and lubrication
RULE-011 | Falla Operativa | Operations | Operational condition | Operations | Monitor Next Stage |  | No | Draft - technical validation required | Classification from Integrated Pump Failure | Adjust operating condition and monitor the next stage
RULE-012 | Filtros de aire saturados | Mechanical | Almost / Consumable | Mechanical | Replace Consumable |  | No | Draft - technical validation required | Classification from Integrated Pump Failure | Replace air filter
RULE-013 | Filtros de aceite saturados | Mechanical | Almost / Consumable | Mechanical | Replace Consumable |  | No | Draft - technical validation required | Classification from Integrated Pump Failure | Replace oil filter
RULE-014 | Pérdida de Fluido | Fluid end | Broken | PE | Repair In-Line |  | Depends | Draft - technical validation required | Classification from Integrated Pump Failure | Isolate leak and repair
RULE-015 | Presión de tapas | Fluid end | Almost / Consumable | PE | Inspect |  | Depends | Draft - technical validation required | Classification from Integrated Pump Failure | Inspect fluid-end caps and pressure
RULE-016 | Émbolo | Fluid end | Broken | PE | Repair In-Line |  | Depends | Draft - technical validation required | Classification from Integrated Pump Failure | Inspect and replace plunger if confirmed
RULE-017 | DME | Unknown | Under diagnosis | Unknown | Diagnose |  | Depends | Draft - technical validation required | Classification from Integrated Pump Failure | Diagnose and assign responsible group

## Catalogs
CONTROLLED CATALOGS — APP DROPDOWNS
CurrentStatus | ConditionClass | DetectionSource | FailureArea | DiagnosisStatus | ResponsibleGroup | YesNo | STTReadiness | PlannedAction | WorkStatus | ResolutionOutcome | ManifoldType | PumpType | FailureReason
Rigged In - Working | Healthy / Available | Manual - Field | Fluid end | Suspected | PE | Yes | Ready | Stay Online | Backlog | Returned to service | Clean | Pumpdown | ACE / Windows / Daisy Data
Rigged In - Not Working | Broken | Octiv | Mechanical | Confirmed | IEM | No | Waiting diagnosis | Inspect | Selected current STT | Replaced | Dirty | Fracturing pump | Actuador Falla Mecánica
Rigged Out - Working | Almost / Consumable | A360 | E-tech / Controls | Discarded | E-Tech |  | Waiting part | Diagnose | In progress | Temporary fix | Off set | Spare | Actuador Falla electrónica
Rigged Out - Not Working | Operational condition | ROCC / Alert | Operations | Under diagnosis | Mechanical |  | Waiting personnel | Repair In-Line | Completed | Deferred |  | Other | Alternador
In Maintenance | Under diagnosis | ACE | Electrical | Not applicable | Operations |  | Exceeds STT window | Replace Consumable | Deferred | No fault found |  |  | A base
Ready |  | DPM | Fuel |  | Supervisor |  | Not required | Rig Out | Not required | Still down |  |  | Baja presión de gasoil
|  | TCM / ECM | Unknown |  | Vendor |  |  | Rig In |  | Not applicable |  |  | Baja presión de lubricante
|  | Engineering Room |  |  | Unknown |  |  | Swap Pump |  |  |  |  | Cavitación
|  | Rule Engine | [5 empty] | Send to Base |  |  |  |  | Convertidor Exceso
[8 empty] | Reset / Reconfigure |  |  |  |  | DME
[8 empty] | Monitor Next Stage |  |  |  |  | Delete
[8 empty] | Unavailable |  |  |  |  | Desprendimiento de clam
[8 empty] | Other |  |  |  |  | Empaque
Extrusión de biela (ventilation)
Falla DPM
Falla Operativa
Falla sensor / instrumentación
Filtros de aceite saturados
Filtros de aire saturados
Fluid End Maintenance
Nivel de aceite incorrecto
Oscilación RPM
Otro
Presión de cárter
Presión de tapas
Pérdida de Fluido
Pérdidas fluído proceso
SIN INFO
Temperatura
Voltaje baterías
Émbolo

## Data_Dictionary
DATA DICTIONARY — FRONT-END / BACKEND CONTRACT
FieldName | Group | Definition | DataType | RequiredRule | PrimarySource | EditableInApp | LandingVisible | SourceMapping / Notes
RecordId | Record & capture | Unique row key. | Text | Required | App / backend | No | No | New technical key.
CaptureId | Record & capture | Groups every pump recorded in the same operational snapshot. | Text | Required | App / backend | No | No | Sean header; LUCTIV capture/export snapshot.
StageExecutionId | Record & capture | Unique key for pad, set, well and stage execution. | Text | Required | App / backend | No | No | New key to prevent duplicate stage ambiguity.
CaptureTimestamp | Record & capture | Date and time when the snapshot was confirmed. | DateTime | Required | App / backend | No | No | CaptureTimestamp / export time.
CapturedBy | Record & capture | User who confirmed the snapshot. | Text | Required | Authentication | No | No | Sean header.
CaseId | Record & capture | Persistent identifier for the same open pump failure across captures. | Text | Conditional: failure case | App / supervisor | Yes | No | New traceability key.
Pad | Stage context | Pad or location identifier. | Text | Required | Octiv / app | No | No | Pad from LUCTIV.
SetId | Stage context | Operational set identifier. | Integer | Required | Octiv / app | No | No | SET from LUCTIV.
SpreadIdentifier | Stage context | Spread identifier. | Text | Required | Octiv | No | No | YPF minimum requirement.
CrewName | Stage context | Crew name. | Text | Required | Octiv / app | No | No | YPF minimum requirement.
Well | Stage context | Well identifier. | Text | Required | Octiv / app | No | No | Well from LUCTIV / YPF requirement.
Stage | Stage context | Fracturing stage number. | Integer | Required | Octiv / app | No | No | Stage from LUCTIV / YPF requirement.
PumpId | Pump configuration | Operational pump SAP identifier; preserve leading zeros. | Text | Required | Octiv | No | Yes | PumpId / PumpSAPID. UI can display the last four digits.
PumpType | Pump configuration | Pump type. | Text | Required | Octiv | No | No | YPF minimum requirement.
Manifold | Pump configuration | Manifold identifier or Spare. | Text | Required | Octiv / app | No | No | Sean header / LUCTIV manifold.
ManifoldType | Pump configuration | Clean, Dirty or Off set. | Text | Required | Octiv / app | No | No | LUCTIV manifold type.
Position | Pump configuration | Pump side and slot or Off set. | Text | Required | Octiv / app | No | Yes | Merged Side + Slot / YPF pump position.
PumpDistance | Pump configuration | Distance value supplied by Octiv. | Decimal | Optional | Octiv | No | No | YPF minimum requirement.
ActuatorNumber | Pump configuration | Associated actuator number. | Text | Optional | Octiv / app | No | No | YPF minimum requirement.
DGB_Bifuel | Pump configuration | Whether the pump uses DGB/Bifuel. | YesNo | Optional | Octiv / app | No | No | YPF minimum requirement.
CurrentStatus | Failure characterization | Current physical and operational status. | Text | Required | Octiv / A360 / supervisor | Conditional | Yes | Standardized from LUCTIV status + in-set state.
ConditionClass | Failure characterization | Broken, near-limit consumable, operational condition, diagnosis, or available. | Text | Required | Rule engine + supervisor | Yes | Yes | Integrated Pump Failure landing classification.
DetectionSource | Failure characterization | System or person that first detected the condition. | Text | Conditional: condition | Octiv / A360 / systems / manual | Yes | No | Integrated detection channels.
FailureDetectedAt | Failure characterization | Time of initial detection, not export time. | DateTime | Conditional: condition | System / supervisor | Yes | No | New event timestamp.
FailureArea | Failure characterization | High-level technical area. | Text | Conditional: condition | Rule engine + supervisor | Yes | No | Integrated High_Level_Area.
FailureReason | Failure characterization | Controlled reason for the fall or degraded condition. | Text | Conditional: condition | Rule engine + supervisor | Yes | Yes | Sean header + Integrated cause taxonomy.
FailureEvidence | Failure characterization | Observed alert, symptom, rate/pressure change or field note. | Text | Conditional: condition | Systems / supervisor | Yes | No | Preserves evidence separate from diagnosis.
DiagnosisStatus | Failure characterization | Suspected, confirmed, discarded or under diagnosis. | Text | Conditional: condition | Supervisor / engineer | Yes | No | New field separating preliminary and final diagnosis.
ResponsibleGroup | Failure characterization | Group expected to intervene. | Text | Conditional: work | Rule engine + supervisor | Yes | Yes | Sean header / YPF high-level down reason workflow.
PartOfPlan | Current STT planning | Yes only for work selected for the current STT. | YesNo | Required | Supervisor | Yes | Yes | Eric requirement / Sean PartOfPlan.
STTOrder | Current STT planning | Execution order inside the selected STT. | Integer | Conditional: PartOfPlan=Yes | Supervisor | Yes | No | Supports 3 selected units while all candidates remain visible.
STTReadiness | Current STT planning | Whether the task is ready and what blocks it. | Text | Required for backlog | Supervisor | Yes | No | New planning control.
PlannedAction | Current STT planning | Action planned before work begins. | Text | Conditional: work | Rule engine + supervisor | Yes | Yes | Sean header.
ReplacementPumpId | Current STT planning | Replacement unit linked to the affected pump. | Text | Optional | Supervisor / A360 | Yes | Yes | Sean header / YPF replacement requirement.
MinutesToRecovery | Current STT planning | Whole-minute recovery estimate. | Integer | Conditional: work | Rule engine + supervisor | Yes | Yes | Sean header / YPF repair estimate.
TaskDescription | Current STT planning | Specific work instruction. | Text | Conditional: work | Rule engine + supervisor | Yes | No | Sean header.
DeferredReason | Current STT planning | Reason the unit remains outside the current STT plan. | Text | Conditional: PartOfPlan=No | Supervisor | Yes | No | Preserves backlog decision.
WorkStatus | Execution & result | Backlog, selected, in progress, completed, deferred or not required. | Text | Required | App / supervisor | Yes | Yes | Integrated Plan_STT workflow.
WorkStartAt | Execution & result | Actual maintenance start time. | DateTime | Conditional: work started | App clock | Yes | No | YPF actual work clock.
WorkEndAt | Execution & result | Actual maintenance end time. | DateTime | Conditional: work ended | App clock | Yes | No | YPF actual work clock.
ActualMinutes | Execution & result | Calculated elapsed minutes between start and end. | Integer | Calculated | Calculated | No | No | Formula from WorkStartAt and WorkEndAt.
ActualAction | Execution & result | Action actually performed. | Text | Conditional: work completed | Supervisor / technician | Yes | No | Separates plan from execution.
ConfirmedFailureReason | Execution & result | Final cause confirmed after intervention. | Text | Conditional: diagnosis complete | Supervisor / engineer | Yes | No | Training target for future Smart Maintenance.
ResolutionOutcome | Execution & result | Final result of the intervention. | Text | Conditional: case updated | Supervisor | Yes | No | Returned, replaced, deferred, still down, etc.
ReturnToServiceAt | Execution & result | Time the pump became available after test/validation. | DateTime | Conditional: returned | App / supervisor | Yes | No | Different from WorkEndAt.
Comments | Execution & result | Operational comments not represented by controlled fields. | Text | Optional | Supervisor / engineer | Yes | No | Sean header.
PumpRate | Real-time operation | Pump rate at capture. | Decimal | Optional | Octiv | No | No | YPF minimum requirement.
PumpPressure | Real-time operation | Pump pressure at capture. | Decimal | Optional | Octiv | No | No | YPF minimum requirement.
CleanRate | Real-time operation | Clean rate at capture. | Decimal | Optional | Octiv | No | No | YPF minimum requirement.
DirtyRate | Real-time operation | Dirty rate at capture. | Decimal | Optional | Octiv | No | No | YPF minimum requirement.
JobRate | Real-time operation | Total job rate at capture. | Decimal | Optional | Octiv | No | No | YPF minimum requirement.
OffsetWellPressure | Real-time operation | Offset-well pressure when available. | Decimal | Optional | Octiv / integration | No | No | YPF minimum requirement candidate.