## Stage_Failure_Summary
LUCTIV V1 PRIME — STAGE FAILURE SUMMARY
PRIME schema version | 1.0
Pad | LAJE
Set | 5
Spread | SPREAD-05
Crew | Crew Argentina
Well | 106
Stage | 51
StageExecutionId | LAJE-SET5-W106-S51
Export timestamp | 46241.0754
Exported by | SupervisorA
Total pumps | 8
Available pumps | 4
Broken pumps | 2
Near-limit pumps | 2
Open cases | 6
Selected STT cases | 2
Closed cases | 0
CaseId | PumpId | FailureDetectedAt | FailureEvidence | FailureReason | ConfirmedFailureReason | DiagnosisStatus | ResponsibleGroup | PartOfPlan | STTOrder | STTReadiness | PlannedAction | ActualAction | MinutesToRecovery | ActualMinutes | ReplacementPumpId | ResolutionOutcome | WorkStatus | ReturnToServiceAt | Comments
CASE-2268-20260805-01 | 2268 | 2026-08-05 17:48 | Unit unavailable; fluid-end maintenance required | Fluid End Maintenance |  | Confirmed | PE | Yes | 1 | Ready | Rig Out |  | 15 |  | 2230 |  | Selected current STT |  | Sale por mantenimiento
CASE-1951-20260805-01 | 1951 | 2026-08-05 17:50 | Packing condition identified during the stage | Empaque |  | Confirmed | PE | Yes | 2 | Ready | Repair In-Line |  | 12 |  |  |  | Selected current STT |  | Maintenance during current STT
CASE-8340-20260805-01 | 8340 | 2026-08-05 16:30 | Unit unavailable and sent for troubleshooting | A base |  | Under diagnosis | IEM | No |  | Exceeds STT window | Send to Base |  | 120 |  |  | Deferred | Deferred |  | Remains visible in backlog
CASE-7720-20260805-01 | 7720 | 2026-08-05 17:20 | Power-end lube oil temperature oscillation warning | Baja presión de lubricante |  | Suspected | Mechanical | No |  | Waiting diagnosis | Inspect | [5 empty] | Backlog |  | Near-limit condition; keep on backlog
CASE-4896-20260805-01 | 4896 | 2026-08-05 17:15 | High well pressure; target rate could not be maintained in the current gear | Falla Operativa |  | Confirmed | Operations | No |  | Not required | Monitor Next Stage | [5 empty] | Backlog |  | Keep visible for operational follow-up
CASE-9800-20260805-01 | 9800 | 2026-08-05 17:42 | DPM discharge sensor failure | Falla sensor / instrumentación |  | Suspected | E-Tech | No |  | Waiting diagnosis | Diagnose | [5 empty] | Backlog |  | Not selected for current STT

## Pump_Stage_Log
RecordId | CaptureId | StageExecutionId | CaptureTimestamp | CapturedBy | CaseId | Pad | SetId | SpreadIdentifier | CrewName | Well | Stage | PumpId | PumpType | Manifold | ManifoldType | Position | PumpDistance | ActuatorNumber | DGB_Bifuel | CurrentStatus | ConditionClass | DetectionSource | FailureDetectedAt | FailureArea | FailureReason | FailureEvidence | DiagnosisStatus | ResponsibleGroup | PartOfPlan | STTOrder | STTReadiness | PlannedAction | ReplacementPumpId | MinutesToRecovery | TaskDescription | DeferredReason | WorkStatus | WorkStartAt | WorkEndAt | ActualMinutes | ActualAction | ConfirmedFailureReason | ResolutionOutcome | ReturnToServiceAt | Comments | PumpRate | PumpPressure | CleanRate | DirtyRate | JobRate | OffsetWellPressure
REC-0051-6672 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA |  | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 6672 | Fracturing pump | MFD-01 | Dirty | Left-05 |  | 22 | No | Rigged In - Working | Healthy / Available | Octiv |  |  |  |  | Not applicable |  | No |  | Not required | Stay Online |  | 0 | Continue operating |  | Not required | [5 empty] | Not applicable |  | Available during current stage | 4.5 | 8000 | 12 | 18 | 30
REC-0051-2268 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-2268-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 2268 | Fracturing pump | MFD-01 | Dirty | Right-06 |  | 12 | No | Rigged In - Not Working | Broken | Manual - Field | 2026-08-05 17:48 | Fluid end | Fluid End Maintenance | Unit unavailable; fluid-end maintenance required | Confirmed | PE | Yes | 1 | Ready | Rig Out | 2230 | 15 | Replace affected pump before the next stage |  | Selected current STT | [7 empty] | Sale por mantenimiento | 0 | 0 | 12 | 18 | 30
REC-0051-1951 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-1951-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 1951 | Fracturing pump | MFC-01 | Clean | Left-07 |  | 31 | No | Rigged In - Not Working | Almost / Consumable | Manual - Field | 2026-08-05 17:50 | Fluid end | Empaque | Packing condition identified during the stage | Confirmed | PE | Yes | 2 | Ready | Repair In-Line |  | 12 | Inspect and replace packing |  | Selected current STT | [7 empty] | Maintenance during current STT | 0 | 0 | 12 | 18 | 30
REC-0051-2230 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-2268-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 2230 | Fracturing pump | Spare | Off set | Off set |  |  | No | Rigged Out - Working | Healthy / Available | A360 |  |  |  |  | Not applicable | PE | Yes | 3 | Ready | Rig In |  | 5 | Replacement pump for Pump 2268 |  | Selected current STT | [7 empty] | Available spare selected for this STT | 0 | 0 | 12 | 18 | 30
REC-0051-8340 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-8340-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 8340 | Fracturing pump | Spare | Off set | Off set |  |  | No | Rigged Out - Not Working | Under diagnosis | Manual - Field | 2026-08-05 16:30 | Unknown | A base | Unit unavailable and sent for troubleshooting | Under diagnosis | IEM | No |  | Exceeds STT window | Send to Base |  | 120 | Unit sent to base for troubleshooting | Estimated recovery exceeds the current STT window | Deferred | [5 empty] | Deferred |  | Remains visible in backlog | 0 | 0 | 12 | 18 | 30
REC-0051-7720 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-7720-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 7720 | Fracturing pump | MFD-02 | Dirty | Left-08 |  |  | No | Rigged In - Working | Almost / Consumable | ACE | 2026-08-05 17:20 | Mechanical | Baja presión de lubricante | Power-end lube oil temperature oscillation warning | Suspected | Mechanical | No |  | Waiting diagnosis | Inspect |  |  | Inspect lubrication condition and confirm diagnosis | Not selected for the current STT | Backlog | [7 empty] | Near-limit condition; keep on backlog | 4 | 7800 | 12 | 18 | 30
REC-0051-4896 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-4896-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 4896 | Fracturing pump | MFD-02 | Dirty | Right-09 |  |  | No | Rigged In - Working | Operational condition | ACE | 2026-08-05 17:15 | Operations | Falla Operativa | High well pressure; target rate could not be maintained in the current gear | Confirmed | Operations | No |  | Not required | Monitor Next Stage |  |  | Adjust operating condition and monitor the next stage | Operational condition; no maintenance selected | Backlog | [7 empty] | Keep visible for operational follow-up | 3.5 | 10200 | 12 | 18 | 30
REC-0051-9800 | CAP-20260805-0051 | LAJE-SET5-W106-S51 | 2026-08-05 18:00 | SupervisorA | CASE-9800-20260805-01 | LAJE | 5 | SPREAD-05 | Crew Argentina | 106 | 51 | 9800 | Fracturing pump | MFC-02 | Clean | Right-10 |  |  | No | Rigged In - Not Working | Broken | DPM | 2026-08-05 17:42 | E-tech / Controls | Falla sensor / instrumentación | DPM discharge sensor failure | Suspected | E-Tech | No |  | Waiting diagnosis | Diagnose |  |  | Inspect DPM sensor, wiring and signal | Waiting diagnosis before assigning STT work | Backlog | [7 empty] | Not selected for current STT | 0 | 0 | 12 | 18 | 30